## Slide 1
SC meeting
R. Aleksan
February 11th. 2011
TIARA
General Information
Final Budget
Meeting Objectives
Organizational matters
Kickoff meeting
Conclusion
TIARA website: http://www.eu-tiara.eu

## Slide 2
TIARA status
Since last TPB meeting
  May 18nd TPB meeting decision
Acceptation of the EC proposed contribution of 3.9 M€
Approval of the reorganisation of the project
Reduce costs of each technical WP by ~20% ,
keeping the main objectives
Reduce globally WP1-6 by ~20%
  with largest reduction coming from WP6
  preferably merge WP6 with WP3
Reduce significantly travel costs
(unit costs =625€ and less travels)
Agreement to keep the matching fund at about the same level as in proposal

## Slide 3
Revised TIARA project
WP leader change: A. Unnervik replaces O. Brunning for WP3
New Total Cost: k€ 9 139
WP1-5: new total cost = k€ 5 758
WP6-9 : new total cost = k€ 3 381

## Slide 4
TIARA status (cont’d)
End June 2010: Approval of the new proposal by the EC
Long discussion with the EC for Third Parties
July 2010: Agreement with the EC to use subcontract instead of TP
Sept. 2010: Final DoW (annex 1) sent to the EC
New issue about IBBA with the EC
Nov 11, 2010: Approval of the DoW by the EC
Dec. 8, 2010: Grant Agreement signed by the EC
Dec. 21, 2010: First prepayment (2 925 k€) sent by the EC
January 1, 2011: Official start date of TIARA
Hiring of Project Coordinator Assistant at CEA
Candidate found: Celine Tanguy, awaiting contract signature

## Slide 5
SC Meeting Objectives
Ensure that the work has effectively started in each WP
Review deliverables/milestones and difficulties if any
Get feedback of proposed first funding transfer to participants
Decide on TIARA organizational matters
Organize kickoff meeting

## Slide 6
Revised Budget
 | Initial Proposal (k€) |  |  | TIARA final budget after negociation with EC (k€) |  | 
Participant | Total costs | EC | Match funds | Total costs | EC | Match funds
CEA | 1603 | 971 | 632 | 1325.8 | 630.5 | 695.3
CERN | 2192 | 931 | 1261 | 1878.5 | 713.8 | 1164.7
CNRS | 939 | 482 | 457 | 682.8 | 299.5 | 383.3
CIEMAT | 458 | 261 | 197 | 365.0 | 166.3 | 198.7
DESY | 611 | 367 | 244 | 284.0 | 138.0 | 146.0
GSI | 342 | 273 | 69 | 267.3 | 164.1 | 103.2
INFN | 1678 | 804 | 874 | 1350.5 | 540.7 | 809.8
PSI | 1610 | 765 | 845 | 1355.3 | 544.0 | 811.3
STFC | 1397 | 613 | 784 | 1090.6 | 414.4 | 676.2
UPPS. | 646 | 318 | 328 | 291.3 | 155.3 | 136.0
IPJ-PAN | 324 | 210 | 114 | 248.0 | 133.4 | 114.6
TOTAL | 11802 | 6000 | 5803 | 9139 | 3900 | 5239
TIARA final budget after negociation with EC (k€) |  | 
WP | Total costs | EC
WP1 | 854 | 401
WP2 | 1 326 | 663
WP3 | 1 674 | 841
WP4 | 986 | 504
WP5 | 918 | 458
WP6 | 1 063 | 348
WP7 | 704 | 179
WP8 | 1 106 | 349
WP9 | 508 | 158
Total | 9139 | 3900

## Slide 7
First year Deliverables
Num | Nat[1] | Short name | Description | month | 
D1.1 | O | OWSF | Overall Web Site Frame ready | 1 | PU
D1.2 | O | CAP | Consortium Agreement between participants ready | 1 | CO
D1.3 | O | CCE | Contract of the Consortium with the EC signed | 1 | CO
D1.4 | O | OKM | Organization of the Kickoff meeting | 1 | CO
D1.5 | O | IWSF | Internal Web Site Frame Ready | 2 | CO
D4.1 | R | KIR | General Report on Key Accelerator Research Areas and Key R&D Issues | 5 | PU
D6.1 | R | D_SLS_NOW | Report on existing hardware limitations and needed upgrades. | 9 | PU
D5.1 | R | ETR | Education and Training Survey Report | 10 | PU
D2.1 | O | MoA-GI | Memorandum of Agreement on General Issues | 12 | CO
D3.1 | R | ISR | Infrastructure Survey Report. | 12 | PU
D1.1: already exists
D1.2: Is written, awaiting approval from CEA legal service prior to sending
to beneficiaries
D1.3: Contract (GA) signed by CEA and EU, awaiting last 3 beneficiary signatures
D1.4: date fixed to 23-24:2/2011 at CERN, organization on going

## Slide 8
First year Milestones
Num | Nat | Short name | Description | month | 
M3.1 | O | NWPC | Nomination of WPC for each ARA. | 1 | CO
M4.1 | O | FSG | Formation of Study Group for Identification of Key Issues | 1 | CO
M1.1 | O | MTR | Monitoring tool and documentation repository | 4 | CO
M4.2 | O | FWG | Formation of Working Groups | 5 | CO
M6.1 | R | M_INSTR | Interim report on existing beam instrumentation | 5 | PU
M2.1 | R | I-GI | Interim Report on General Issues | 6 | CO
M5.1 | O | METR | Meeting to plan ETR report | 7 | CO
M3.2 | R | ISR | Interim Infrastructure Survey Report | 8 | CO
M7.1 | R | RFSysReq | Report on RF system layout and requirements | 8 | PU
M8.1 | O | HARDW-A | Purchase of crucial hardware components | 9 | PU
M5.2 | O | METD | Meeting to plan ETD database | 11 | CO
M2.3 | R | I-CDO | Interim Report on Communication, Dissemination and Outreach | 12 | CO
M9.1 | R | DSIF | Definition and Specifications of the Irradiation test Facilities | 12 | PU

## Slide 9
Revised detailed budget
 | TIARA final budget after negociation with EC (k€) |  | 
Participant | Total costs | EC | First transfer
CEA | 1325.8 | 630.5 | 236 437,50
CERN | 1878.5 | 713.8 | 267 675,00
CNRS | 682.8 | 299.5 | 112 297,50
CIEMAT | 365.0 | 166.3 | 62 347,50
DESY | 284.0 | 138.0 | 51 738,75
GSI | 267.3 | 164.1 | 61 552,50
INFN | 1350.5 | 540.7 | 202 773,75
PSI | 1355.3 | 544.0 | 203 985,00
STFC | 1090.6 | 414.4 | 155 418,75
UPPS. | 291.3 | 155.3 | 58 233,75
IPJ-PAN | 248.0 | 133.4 | 50 040,00
TOTAL | 9139 | 3900 | 1 462 500,00

## Slide 10
Organization matters
Reporting
TIARA internal reporting
Steering Committee meetings (at least 3 per year)
  Proposal: January/February, May/June, September/October
Biannual written reports
  Proposal: June and December
Individual phone discussions with WP leaders as needed
TIARA « official » reporting
Governing Council Meetings ( at least 1 per year)
  Proposal: February 2011, following ones tbd with GC
General TIARA meetings (in connection to 18 month report
  Proposal: May 2012 and November 2013
18 month written reports
  Proposal: June 2012 and December 2013
Mid-term review
  Tbd with the EC scientific officer

## Slide 11
Organization matters (cont’d)
Documentation
TIARA documentation database for all types of TIARA documents
Publications, Reports, Notes, Conference papers, Thesis…
(see CARE model)
TIARA Progress indicator
Milestones/deliverables tables (see CARE model)
Chart: Scheduled deliverables vs months
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Integral scheduled deliverables | 0 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 8 | 8 | 10 | 10 | 11 | 12 | 13 | 13 | 16 | 16 | 16 | 16 | 17 | 17 | 24 | 24 | 24 | 24 | 24 | 25 | 27 | 27 | 27 | 33 | 35 | 36 | 41

## Slide 12
TIARA Kickoff meeting
Date: February 23-24, 2011
Meeting format: It is essentially a work meeting
Meeting Room reservations
Feb. 23:
11:00-12:30 : Governing Board meeting
14:00-15:30 : Plenary session (general TIARA informations)
16:00-18:30 : Parallel sessions for the Work Packages activities
Feb. 24:
8:30-10:30 : Parallel sessions for the Work Packages activities
11:00-12:30 : Plenary session (Reports from the Work Packages)
14:00-17:00 : Plenary session (Reports from the WP packages)
8 rooms have been reserved for parallel sessions
Rooms: 4/3-021, 60/2-023, 61/1-017, 61/1-007, 14/4-002, 72/1-020, 72/R-036, 5/5-008 (tbc)
Any special wish from WP leaders?

## Slide 13
TIARA Kickoff meeting (cont’d)
Hostel room reservations
Web site
60 CERN hostel rooms prereserved with deadline on 20/01/2011
Beeing done, should be ready this week
TIARA Dinner
We are planning to organize a TIARA dinner on evening 23/2/2011
Local responsible persons for the meeting
Anders Unnervik and Nathalie Gouriou (secretary)

## Slide 14
Conclusions
Accelerator science;
a powerful mean toward scientific, technical
and industrial breakthroughs…
TIARA will strengthen further
The objectives of TIARA are very ambitious and challenging
TIARA-PP has started! It is our common task to make it a success and ensure the sustainability of accelerator R&D